## Hoja 1
Methodology: | [6 empty] | Metodología
Goal | Objective | Dates | Activities | Tools | Results | Demonstration | Objetivos |  | Fechas | Lugar | Actividades | Herramientas | Resultados | Demostración
1 | 1.1 | JAN-JUN 2025 | Perform data analysis Identify features in clinical data that impact cellular metabolism, looking through literature and applying ML algorithms such as K-means to analyze patterns | Computer equipment and databases | Significant data to integrate into GEM models | Metabolic flux analysis in patient-specific GEM models with integrated clinical data and adapted tumor microenvironment | 1 | 1.1 | ENE-JUN 2025 | CUCEI | Realizar análisis de datos para identificar características en datos clínicos que impactan el metabolismo celular, buscando en la literatura y aplicando algoritmos de ML, como k means, para analizar patrones | Equipo de cómputo y bases de datos | Datos significativos para integrar en modelos MEGs | Análisis de flujos metabólicos en modelos GEM específicos para pacientes con datos clínicos integrados y microambiente tumoral adaptado
| 1.2 |  | Development of GEMs through the integration of clinical data | Computing equipment, MATLAB, and COBRA Toolbox | Patient-specific GEMs |  |  | 1.2 |  |  | Desarrollar modelos de redes metabólicas (GEMs) mediante la integración de datos clínicos | Equipo de cómputo, MATLAB y COBRA Toolbox | MEGs específicos para pacientes.
2 | 2.1 | JUN-NOV 2025 | Adapt metabolic models to the specific characteristics of the tumor microenvironment to improve their accuracy | Computing equipment and use of statistical methods | Correlations between metabolic phenotypes and specific clinical characteristics |  | 2 | 2.1 | JUN-NOV 2025 | CUCEI | Adaptar los modelos metabólicos a las características específicas del microambiente tumoral para mejorar su precisión |  | MEGs adaptados al microambiente tumoral
| 2.2 |  | Correlate metabolic phenotypes with the patient's clinical characteristics | Computing equipment, Python, machine learning, and evaluation metrics | Machine learning models with high predictive capacity for metabolic phenotypes | Graphs with significant correlations |  | 2.2 |  | ALEMANIA | Correlacionar fenotipos metabólicos con características clínicas del paciente | Equipos de cómputo, Python, metodos estadisticos aprendizaje automático y métricas de evaluación | Correlaciones entre fenotipos metabólicos y características clínicas específicas | Gráficas con correlaciones significativas
[7 empty] | This work: |  |  |  | Yes/No | Which one
[7 empty] | Is this part of a larger project? Which one? |  |  |  | Yes | Cell-Ai: It is a Python repository focused on personalized medicine. The developed code will be shared in a GitHub repository (https://github.com/GIMIudg/cellAI)
[7 empty] | Is this project a continuation of a previous one? Which one? |  |  |  | No | Cell-Ai consists of several independent projects focused on personalized medicine. The project will be carried out in collaboration with researchers from the University of Guadalajara and the Western Biomedical Research Center (CIBO), which will provide the necessary clinical data
[7 empty] | Are you carrying out the project in collaboration with anyone else? With whom? |  |  |  | No | -
[7 empty] | Does the project have the necessary infrastructure to carry it out? Is additional infrastructure required? |  |  |  | Yes | This project is funded by the National Council for Humanities, Sciences, and Technologies
[7 empty] | Does the project have the necessary infrastructure to carry it out? Is additional infrastructure required? |  |  |  | Yes | The required resources include a high-capacity personal computer and a stable internet connection for the development of machine learning models and GEMs

## Hoja 2
Cronomagrama:
Objetivo | Actividad | 2025
|  | ENE | FEB | MAR | ABR | MAY | JUN | JUL | AGO | SEPT | OCT | NOV | DIC
Actividad de retribución social realizada en Octubre del 2024 en la feria de posgrados de CUCEI
2024-01-01 | Estudio del estado del arte
Recolectar y preprocesar datos clínicos de pacientes con cáncer de mama para su integración en el análisis. | bar: 2025 ENE to 2025 ABR
2024-02-01 | Diseñar y construir modelos metabólicos a escala genómica (MEGs) personalizados que incorporen información clínica asociada a la progresión y/o pronóstico del cáncer | bar: 2025 FEB to 2025 ABR
2024-01-02 | Adaptar los modelos metabólicos a las características específicas del microambiente tumoral para mejorar su precisión. | bar: 2025 ABR to 2025 JUL
Actividad complementaria: Intercambio académico en Alemania y posible presentacion de resultados en congreso | bar: 2025 SEPT to 2025 DIC
2.2 | Realizar análisis estadísticos y aplicar modelos de machine learning, como SVM, redes neuronales y K-means, para identificar patrones y correlaciones en los datos clínicos | bar: 2025 JUL to 2025 SEPT
Representación de resultados en graficos | bar: 2025 SEPT to 2025 NOV
Elaboración y redacción de tesis | bar: 2025 MAY to 2025 DIC
Timeline
Objective | Activity | 2025 ENE: 2025
|  | ENE | FEB | MAR | ABR | MAY | JUN | JUL | AGO | SEPT | OCT | NOV | DIC
Social contribution activity carried out in October 2024 at the CUCEI postgraduate fair
2024-01-01 | State-of-the-art study
Collect and preprocess clinical data from breast cancer patients for integration into the analysis. | bar: 2025 ENE to 2025 ABR
2024-02-01 | Design and build personalized genome-scale metabolic models (MEGs) incorporating clinical information associated with cancer progression and/or prognosis | bar: 2025 FEB to 2025 ABR
2024-01-02 | Adapt metabolic models to the specific characteristics of the tumor microenvironment to improve their accuracy | bar: 2025 ABR to 2025 JUL
Complementary activity: Academic exchange in Germany and possible presentation of results at a conference | bar: 2025 SEPT to 2025 DIC
2.2 | Perform statistical analyses and apply machine learning models, such as SVM, neural networks, and K-means, to identify patterns and correlations in clinical data | bar: 2025 JUL to 2025 SEPT
Representation of results in graphs | bar: 2025 SEPT to 2025 NOV
Thesis writing and preparation | bar: 2025 MAY to 2025 DIC